## Sheet1
Item | Description | Person Assigned | Complete (Yes / No)
2 Security Folders | There are currently 2 Security folders with the same code - consolidate | Saideepak | No
Authorization | Add authorization so people have to login | Saideepak | No
Calendar | Put Calendar view into build
Consistent look and feel |  | Leona | No
Produce mockups for screens | Provide mockups for all screens | Toby | No
Deployment and Packaging | Make this portable and deployable on a web server | Saideepak | No
Controller.js has worker conrol in it | Move to workersController.js? | Saideepak | No
dbConnectionsController in both DAO and routes | Is this duplication? yes. | saideepak | No
Build Install script for app | allow this to be deployed onto a clean linux VM | Toby | No
add in skills dropdown to workers form and integrate to REST API | integrate into the skills API and test | Leona | No
add in skills dropdown to job form and integrate to REST API |  | Leona | No